MAHARAJAH INDIA CUISINE

Maharajah Meal Prep

Menu Deconstruction, Market Analysis, Fusion Expansion & Business Proposal

A staged launch plan for separate vegetarian and nonvegetarian weekly meal-prep programs

| Restaurant | Market | Prepared |
| --- | --- | --- |
| 1091 S. Mt. Vernon Ave., Suite G Colton, California 92324 | Colton • San Bernardino • Loma Linda • Redlands • Riverside corridor | August 8, 2026 Decision-ready feasibility study |

INVESTMENT RECOMMENDATION Authorize a pilot cap of $30,000 within a $16,000–$37,000 pilot range. Carve out no more than $3,000–$8,000 for a two-SKU Indo-Mex test rather than increasing the cap. Release standard-scale capital only after four consecutive weeks above 300 meals, safe cooling validation, at least $3.50 contribution per meal after paid production labor, and at least 60% eight-week reorder/retention.

Prepared from public menu data, current competitor pricing, official California and San Bernardino County guidance, and an explicitly assumption-based operating model. Kitchen recipes, costs, capacity, permits, tax treatment, and shelf life require owner, chef, regulator, CPA, and insurer validation before launch.

# Executive decision

RECOMMENDATION: PROCEED, BUT AS A STAGE-GATED PILOT Maharajah has a credible right to win: an established Indian brand, a large vegetarian repertoire, direct online ordering, delivery, rewards, catering capability, and sauces that batch efficiently. The venture becomes attractive only if menu complexity is cut sharply and the line proves repeat demand at roughly 300–320 meals per week.

The public menu contains 135 non-Popular listings across 16 categories and about 129 distinct visible names, yet only about 42 listings have a written description. Multiple duplicate labels, conflicting prices, mislabeled internal item slugs, and missing allergen/portion information make the current menu unsuitable for direct replication into a meal-prep storefront. [2] The operational answer is a 12-SKU weekly rotation drawn from eight batch components—not 129 separate recipes.

| Decision metric | Planning result | Interpretation |
| --- | --- | --- |
| Pilot capital | $16k–$37k; recommend $30k cap | Uses the existing kitchen only if the cooling-load test passes |
| Standard cumulative capital | $50k–$120k | Release only after sustained demand and safe production are proven |
| Blended realized price | About $12.30/meal | Assumes 40% vegetarian / 60% meat and bundle discounting |
| Blended variable cost | About $8.21/meal | Includes ingredients, packaging, direct labor, processing, waste and small delivery subsidy |
| Contribution | $4.09/meal; 33.3% | After paid production labor; fixed overhead remains to be covered |
| Standard break-even | About 319 meals/week | At $5,650 monthly incremental fixed cost |
| Base Year 1 | $271.6k revenue; $25.7k line EBITDA | Ramps from 150 to 700 meals/week |
| Base month-12 run rate | About $81k annualized line EBITDA | Requires retention and the 700-meal/week pace to continue |

Financial outputs are pro forma estimates before depreciation, debt, income tax, startup capital and owner distributions—not guarantees.

## What makes the concept defensible

Authenticity plus convenience: few immediate-area providers visibly combine fresh Indian food, nutrition/portion transparency, single-serving weekly plans, and clear local delivery pricing.

A vegetarian advantage: Maharajah already has lentil, chickpea, vegetable and paneer dishes with strong chilled/frozen quality, not merely one token vegetarian option.

Production leverage: curry, masala, korma, saag, vindaloo, makhani, dal/channa and biryani/tandoori components can power paired vegetarian and meat SKUs.

Owned audience and direct channel: the current site advertises direct ordering, delivery, rewards, mobile app access and catering. [1][4]

A manageable customer target: 60 households averaging ten meals equal 600 meals per week; success depends more on retention than on broad geographic reach.

## Non-negotiable launch conditions

Obtain written County approval for the changed menu/process, packaging, cooling, cold storage, labels and delivery route before major equipment purchases.

Standardize gram-weighted recipes, yields, ingredient costs and allergen declarations; do not rely on public website or third-party descriptions as recipe records.

Pass a worst-case cooling-load test for rice and curry before selling the first box.

Use a Fresh 4 + Frozen remainder model or split delivery; do not promise seven refrigerated days without validated shelf-life evidence.

Keep at least 85% of subscription orders direct; marketplace commissions can erase most modeled contribution.

# 1. Restaurant and digital-menu audit

Maharajah presents itself as a family-owned Inland Empire restaurant with nearly four decades of history. It operates daily from 11:00 a.m. to 9:00 p.m. and supports dine-in, takeout, delivery, reservations, rewards, a mobile app and catering. The site explicitly advertises vegan options, while individual menu items are not labeled vegan. Catering is positioned for corporate events, weddings, private parties and holidays. [1][3][4]

## Current assets

| Asset | Why it matters for meal prep |
| --- | --- |
| Existing commercial kitchen and staff | Avoids a commissary lease in the pilot, subject to County approval and spare cooling/storage capacity |
| Broad North and South Indian menu | Supports rotation and differentiation, but must be condensed |
| Direct online ordering, delivery and rewards | Reduces launch friction and supports direct-order retention |
| Catering experience | Shows batch-production familiarity, though refrigerated meal production is a different process |
| Vegetarian, paneer, lentil and chickpea depth | Creates a real vegetarian product line with better food-cost potential |
| Tandoor and biryani capability | Creates premium and performance-oriented add-ons |

## Digital-menu cleanup required before launch

A duplicate Chicken Curry listing points to an internal Andhra Chicken Fry slug.

Hyderabadi Chicken Biryani appears at $16.64 and $12.48; the lower-price SKU is internally a weekend special.

A $14.56 Channa Masala listing points internally to Chole Bhatura.

Three Chicken Tikka Dry rows represent different internal products; Tikka Dry $17.91 is actually lamb.

Chicken Shish Kabob appears in two categories.

The official menu says meat samosa contains chicken; a third-party listing says beef. This must be reconciled before labeling.

Portion weights, included sides, spice levels, calories, allergens, vegan status, reheating instructions and lot/date information are absent.

Audit based primarily on the official direct menu; the third-party page was used only to identify conflicts and possible ingredients requiring kitchen verification. [2][5]

## Strategic diagnosis

| Strengths | Weaknesses | Opportunities | Threats |
| --- | --- | --- | --- |
| Established brand; direct channel; broad vegetarian line; sauce reuse; catering; tandoor/biryani differentiation | Menu sprawl; duplicate data; no validated allergen/macros; unknown spare cooling capacity; daily restaurant schedule | Healthcare/university/employer drops; Indian weekly subscriptions; vegetarian retention; premium high-protein add-ons | Labor cost; rice/curry cooling risk; low-price frozen meals; tiffin substitutes; delivery leakage; restaurant cannibalization |

# 2. Menu and ingredient deconstruction

Most menu recipes are not published. Ingredient statements below are a kitchen-validation map, not authoritative recipes. “Official” means stated on Maharajah’s website; “secondary” means a third-party description that must be checked; “inferred” means standard culinary composition suggested by the dish name. No allergen, vegan or gluten-free claim should be made from this analysis alone.

| Production family | Current dishes | Likely basis—verify with chef | Risk / prep fit |
| --- | --- | --- | --- |
| House curry | Chicken, lamb, beef, potato curry | Likely onion-tomato, ginger, garlic, oil/ghee, cumin, coriander, turmeric and garam masala | Possible milk/ghee and tree nuts; High fit |
| Masala | Chicken masala; shrimp/fish/vegetable/mushroom/channa masala | Tomato-onion-herb-spice base; channa recipe publicly confirms chickpea and tomato | Likely tree nuts in several recipes; High fit; seafood short-dated |
| Korma | Chicken, lamb, beef, vegetable korma | Likely yogurt/cream, nuts, aromatic spices, possibly coconut | Milk + tree nuts; High fit |
| Saag | Chicken, lamb, beef, shrimp, fish, paneer, aloo, channa | Spinach/greens with onion, tomato, herbs and spices; Aloo Saag publicly includes cream | Milk possible/likely; seafood short-dated; High fit |
| Vindaloo | Chicken, lamb, beef, shrimp, fish | Likely chili-acid-garlic sauce; third-party descriptions suggest cashew/nuts in current recipes | Tree nuts possible; spicy; High fit except seafood |
| Makhani / tikka | Butter chicken, chicken/paneer tikka masala, malai kofta | Tomato, cream/butter, aromatic spices and likely cashew; kofta is fried potato-based | Milk + tree nuts; kofta may contain wheat; High fit |
| Keema | Chicken/beef keema, keema naan, meat samosa | Ground meat, onion and spices; meat identity conflict in samosa | Wheat in naan/samosa; curry High fit |
| Biryani | Chicken, lamb, beef, shrimp, vegetable, Hyderabadi | Basmati rice, spice, onion/herbs and protein/vegetable; possible yogurt/ghee | Rapid cooling critical; milk/nuts possible; shrimp allergen; High fit |
| Tandoori / kebab | Paneer, chicken, lamb and shrimp items | Marinated protein roasted in tandoor with onion, pepper and lime; yogurt marinade likely | Milk likely; can dry on reheating; Moderate fit |
| Pakoda / bonda / vada | All fritters | Gram/lentil flours, vegetables or protein, spices and shared frying oil | Milk/fish on named items; fryer cross-contact; Low fit |
| Samosa / chaat | Meat/vegetable samosa, samosa chaat | Wheat pastry and spiced filling; chaat adds channa, yogurt and chutneys | Wheat + milk; Low fit assembled |
| Dosa / idli / uttapam | South Indian crepes and steamed cakes | Rice/lentil batters; rava versions use semolina; cheese and egg variants as named | Wheat in rava; milk/egg as named; Low dosa fit, Moderate idli fit |
| Sambar / rasam | Soups and combination plates | Lentil-vegetable sambar; likely tamarind-spice rasam | Verify asafoetida/wheat and chutney allergens; High separated fit |
| Bread | Poori, paratha, naan, kulcha, roti, papadam | Wheat breads except likely lentil papadam; dairy/egg/ghee recipe-dependent | Wheat; possible milk/egg; Low chilled, Moderate frozen separately |
| Cold sides | Raita, yogurt, salad, pickle, onion/chili, chutney | Serve in separate cold cups | Milk, dressing egg/milk, possible peanuts/tree nuts; Moderate |
| Lassi / milk drinks | Four lassis and milk-style tea/coffee | Yogurt or milk with fruit/flavorings | Milk; cold-only |
| Desserts | Kulfi, gulab jamun, kheer | Milk-forward desserts; nuts common; gulab jamun likely milk solids/wheat | Milk, tree nuts, likely wheat; separate/frozen |

Major allergen framework: milk, egg, fish, crustacean shellfish, qualifying tree nuts, peanuts, wheat, soy and sesame. [6]

## Eight-component production architecture

House curry base

Nut-tomato masala base

Korma base

Saag base

Vindaloo base

Makhani / tikka-masala base

Dal and channa line

Biryani base plus tandoori marinade

This architecture supports paired vegetarian and meat SKUs while keeping batch count manageable. Vegetarian and meat production still need separate, clearly labeled utensils, storage and production sequencing. Nut-containing and nut-free recipes require deliberate controls; the business should not claim a nut-free kitchen.

## What belongs in meal prep—and what does not

| Launch core | Conditional / premium | Same-day add-on only |
| --- | --- | --- |
| Dal, channa, aloo gobi, baingan bharta, vegetable masala/korma, paneer in sauce, curries, saag, vindaloo, keema, non-seafood biryani | Tandoori chicken/kebabs with sauce; mushrooms; seafood; cream/coconut sauces after freeze-thaw testing; idli packed separately | Pakoda, samosa, bonda, vada, fish fry, dosa, uttapam, poori, assembled chaat, dressed salad and most fresh breads |

# 3. New meal-prep product line

PROPOSED CUSTOMER-FACING NAME Maharajah Weekly — Royal Indian Meal Prep. One brand, two separate menus: Vegetarian and Nonvegetarian. Plans differ by weekly quantity, not by lower food quality.

## Base product specification

One 14–18 oz complete meal in a freezer-safe, tamper-evident tray.

Measured protein-bearing component, vegetables and a controlled serving of basmati rice or two rotis.

Design target of roughly 400–650 calories for core meals; no calorie or protein claim until each standardized recipe is analyzed.

One default spice profile at pilot, with a separate hot chutney option; avoid custom batch fragmentation.

Every label carries full ingredients, major allergens, net quantity, lot code, pack/use-by dates, cold-storage and reheating instructions.

Fresh 4 + Frozen remainder or two weekly drops; do not market a seven-day refrigerator life without validation.

## Three vegetarian tiers

| Plan | Meals | Weekly price | Per meal | Promise |
| --- | --- | --- | --- | --- |
| 5-Day Starter | 5 | $59.95 | $11.99 | Low-commitment trial; choose any five current-week vegetarian meals |
| 10-Meal Routine | 10 | $109.90 | $10.99 | Best-value anchor; free first local delivery or pickup |
| 15-Meal Complete | 15 | $157.35 | $10.49 | Highest-volume plan; split delivery or frozen remainder required |

### Vegetarian four-week launch rotation

| Week | Core choices | Premium choices / upgrades |
| --- | --- | --- |
| 1 | Dal Curry; Channa Masala; Aloo Gobi; Channa Saag; Vegetable Biryani | Saag Paneer +$1; Paneer Tikka Masala +$1 |
| 2 | Dal Makhani; Baingan Bharta; Vegetable Masala; Aloo Matar; Vegetable Korma | Matar Paneer +$1; Paneer Tikka Dry +$1 |
| 3 | Dal Curry; Channa Saag; Mushroom Masala; Aloo Saag; Vegetable Biryani | Paneer Tikka Masala +$1; Saag Paneer +$1 |
| 4 | Channa Masala; Aloo Gobi; Potato Curry; Baingan Bharta; Vegetable Korma | Tandoori Paneer Power portion +$3.49; paneer add-on +$1 |

Vegan-style recipes may be possible for selected dal, channa, aloo gobi and baingan dishes only after ghee, cream, yogurt, nut, supplier and cross-contact review. “Vegetarian” must never be used as a substitute for vegan or allergen-safe.

## Three nonvegetarian tiers

| Plan | Meals | Weekly price | Per meal | Promise |
| --- | --- | --- | --- | --- |
| 5-Day Starter | 5 | $69.95 | $13.99 | Low-commitment trial; standard chicken/beef choices |
| 10-Meal Routine | 10 | $129.90 | $12.99 | Best-value anchor; free first local delivery or pickup |
| 15-Meal Complete | 15 | $187.35 | $12.49 | Highest-volume plan; split delivery or frozen remainder required |

### Nonvegetarian four-week launch rotation

| Week | Core choices | Premium choices / upgrades |
| --- | --- | --- |
| 1 | Chicken Curry; Chicken Masala; Chicken Saag; Chicken Biryani; Tandoori Chicken | Lamb Curry +$3; Shrimp Masala +$2 |
| 2 | Chicken Korma; Butter Chicken; Chicken Vindaloo; Chicken Keema; Hyderabadi Chicken Biryani | Beef Korma +$1; Fish Masala +$2 |
| 3 | Chicken Tikka Masala; Chicken Curry; Chicken Tikka Dry; Beef Curry; Beef Keema | Lamb Saag +$3; Tandoori Shrimp +$2 |
| 4 | Chicken Saag; Chicken Masala; Chicken Shish Kabob; Chicken Biryani; Beef Vindaloo | Lamb Korma +$3; Fish Vindaloo +$2 |

## Add-ons and margin protection

| Add-on | Price | Reason |
| --- | --- | --- |
| Paneer premium | +$1.00 | Protects dairy/ingredient cost |
| High-protein 7 oz chicken or paneer portion | +$3.49 | Matches local premium-protein upgrade logic |
| Cauliflower rice or specialty biryani | +$1.00 | Covers added ingredient and prep cost |
| Shrimp or fish | +$2.00 | Short-dated premium protein |
| Lamb or goat | +$3.00 | Avoids diluting standard meat margin |
| Two rotis or one naan | +$2.49 | Packed separately; freezer/reheat instructions |
| Raita or chutney cup | +$1.00–$1.50 | Separate cold component; allergen-labeled |

# 4. Fusion expansion strategy

RECOMMENDATION: INDO-MEX STORY, CALIFORNIA BOWL SYSTEM Launch a tightly controlled Maharajah Masala Street pilot: two rotating Indian-Mexican bowls inside the existing 12-SKU meal-prep lineup, plus no more than two same-day street-food items after bowl execution is stable. Keep Indian recipes as the production engine. Use familiar California bowl, taco and burrito formats as the customer-facing layer. Do not build a second Mexican kitchen or a full Mediterranean line.

## What the local market suggests

| Colton signal | Current measure | Commercial implication—not proof of demand |
| --- | --- | --- |
| Population | 53,383 | Large enough for a neighborhood pilot; route economics still depend on repeat customers and dense drops |
| Hispanic or Latino | 75.2% | Tacos, burritos, bowls and family packs are familiar formats; paid testing must determine whether customers want an Indian interpretation |
| Language other than English at home | 55.2% | Use professionally proofread English/Spanish menu descriptions and ordering instructions |
| Persons per household | 3.16 | Family kits and multi-meal bundles fit local household structure |
| Median household income / poverty | $71,208 / 13.7% | Keep core individual items around $12.49–$15.49 and reserve lamb, goat and avocado for surcharges |
| Mean commute | 27.5 minutes | Reheatable bowls, grab-and-go pickup and workplace drops solve a plausible convenience need |
| Health-sector demand node | >4,000 ARMC employees | ARMC/CUSM create a nearby audience for tastings, subscriptions and consolidated workplace delivery |

Census values are the latest displayed 2020–2024 ACS/2025 estimate data. Demographic identity must not be treated as preference; it identifies a testable format hypothesis only. ARMC staffing and CUSM class information come from institutional sources. [26][43][44]

## Competitive white space and price anchors

| Observed set | Current signal | Meaning for Maharajah |
| --- | --- | --- |
| Conventional Mexican in Colton | El Rey classic burrito $11.99; veggie burrito $10.99; local tacos generally start near $3 | Proven familiarity but dense competition and a low commodity-taco price anchor; do not imitate a taqueria |
| Indo-Mex | No clearly branded operator surfaced in the Colton/San Bernardino/Riverside direct-menu review | A plausible white space, not proof; Appu's and Saucy Chick show that Southern California customers understand the combination |
| Mediterranean in Colton | Chick-N-Falafel already markets shawarma/falafel bowls, wraps, vegan options, delivery and catering | A capable Maharajah version would overlap an existing same-city position |
| Regional Mediterranean | Baladi bowls $13.95; Luna Grill bowls $17.29–$18.79 | Better premium price corridor than conventional Mexican, but weaker differentiation and more cold-component complexity |

Direct/public menus checked August 8, 2026; public discovery is not exhaustive and prices can change. [45]–[51]

## Concept scorecard

The decision model weights audience fit 25%, competitive white space 20%, ingredient reuse 20%, meal-prep durability 15%, and price/margin plus launch simplicity 20%. Scores are structured operating judgment based on public evidence—not measured demand.

| Concept | Audience 25 | White space 20 | Reuse 20 | Prep fit 15 | Price + simplicity 20 | Total 100 |
| --- | --- | --- | --- | --- | --- | --- |
| Indian–Mexican, bowl-first | 25.0 | 18.0 | 18.0 | 13.5 | 18.0 | 92.5 |
| Indian–California wellness bowls | 20.0 | 14.0 | 20.0 | 15.0 | 17.0 | 86.0 |
| Indian–Mediterranean | 17.5 | 10.0 | 20.0 | 12.0 | 18.0 | 77.5 |
| Indian pizza / wings | 20.0 | 10.0 | 12.0 | 7.5 | 12.0 | 61.5 |

HOW TO READ THE WINNER The permanent operating chassis is an Indian-California portion-controlled bowl: stable, measurable and efficient. The more distinctive customer-facing story is Indian-Mexican. Combining those two ideas produces the strongest balance of local relevance, reheating quality and kitchen reuse.

## Build a sub-line, not a second restaurant

| Layer | Customer promise | Operating rule |
| --- | --- | --- |
| Parent brand | Maharajah quality and Indian culinary credibility | Traditional Indian menu remains intact; fusion is clearly labeled as a separate sub-menu |
| Sub-line | Maharajah Masala Street — Indian flavor in familiar California street-bowl formats | Two rotating weekly meal-prep slots replace two standard slots; never exceed 12 total weekly meal-prep SKUs during the test |
| Meal-prep format | Portion-controlled bowls with hot and cold components separated | Four hot fillings maximum, one basmati base, one cold garnish kit and two finishing sauces |
| Restaurant halo | Fresh tacos, one burrito and eventually a family kit | Same components as bowls; launch only after bowl accuracy, speed and cold holding are stable |

## Recommended four-bowl expansion menu

| Product | Type | Composition | Pickup | Meal-plan treatment |
| --- | --- | --- | --- | --- |
| Channa Masala Street Bowl | Veg | Channa, basmati, roasted corn, cabbage, tomato-onion-cilantro relish, lime and chutney | $12.99 | +$1 fusion test |
| Paneer Tikka Fajita Bowl | Veg | Paneer tikka, peppers/onions, basmati, corn, relish and mint-lime yogurt | $14.49 | +$1 paneer premium |
| Tandoori Chicken Street Bowl | Meat | Tandoori chicken, peppers/onions, basmati, cabbage, corn, relish and chutney | $14.99 | +$1 fusion test |
| Chicken Keema Masala Bowl | Meat | Chicken keema, basmati, cabbage, tomato relish and controlled spicy-tomato chutney | $14.99 | +$1 fusion test |

Do not create a seventh subscription price card. The existing 5/10/15 vegetarian and nonvegetarian tiers remain the base; use the temporary fusion/paneer surcharge until recipe costs prove that inclusion still delivers at least $4.25 contribution per fusion meal.

## Restaurant-only halo products

| Item | Target direct price | Channel rule |
| --- | --- | --- |
| Three paneer tikka street tacos | $13.49–$13.99 | Fresh restaurant/pickup only; corn tortillas and cold garnish packed separately for delivery |
| Three tandoori chicken street tacos | $14.49 | Fresh restaurant/pickup only; do not compare with commodity $3 tacos |
| Tandoori chicken masala burrito | $15.49 | Same-day only; use dry protein and a controlled sauce portion |
| Deconstructed family taco kit | $49.99 veg / $54.99 chicken | Add only after yields and assembly time are verified; designed for approximately four to six |
| Separate tortilla pack | $1.49 | Optional with meal-prep bowls so the customer assembles at home |
| Guacamole cup | +$1.50–$2.00 | Optional phase-two add-on; never embedded in the base cost |

Assembled tacos, wet burritos, nachos and fried shells are not multi-day meal-prep products. Tortillas, slaw, raita and salsa should travel separately. “Vegan” and “gluten-free” claims require recipe, supplier and cross-contact verification.

## Ingredient and equipment crosswalk

| Existing Maharajah component | Fusion use | Net-new need / control |
| --- | --- | --- |
| Tandoori chicken / chicken tikka dry | Bowls, tacos and burrito | Purchased tortillas, cabbage, corn and lime; dry protein protects holding quality |
| Paneer tikka / paneer tikka dry | Vegetarian bowl and tacos | Same garnish system; verify milk and any cashew/tree-nut sub-ingredients |
| Chicken keema | Stable reheatable bowl filling | Portion oil and sauce; no new hot process |
| Channa masala | Vegetarian protein and bean role | Avoid adding black/pinto beans during the first test |
| Basmati rice | Universal bowl/burrito base | Finish with existing cilantro plus lime; do not add a second Mexican rice |
| Onion, tomato, cilantro, peppers | Relish and fajita-style vegetables | Add lime and jalapeño; do not claim Mexican authenticity |
| Mint chutney, spicy tomato chutney, raita | Green finish, masala roja and crema | Two sauces maximum; cold dairy in a separate labeled cup |
| Tandoor, ranges, rice production and cold prep | All hot/cold production | Audit spare capacity; add small cold pans, scoops, scales and a tortilla warmer only if approved |

## Opening-inventory discipline

Start with approximately six core additions: six-inch corn tortillas, twelve-inch flour tortillas, shredded cabbage, frozen/canned corn, limes and jalapeños. Chipotle may be a seventh shelf-stable test. Every new ingredient must serve at least two SKUs. Do not launch with black beans, Mexican rice, guacamole, cotija, fries, chips or several bottled sauces; channa, paneer, yogurt and Maharajah chutneys already perform those flavor/texture roles.

## Why Mediterranean is the runner-up

| Decision factor | Indian–Mexican | Indian–Mediterranean |
| --- | --- | --- |
| Local customer cue | Highest: familiar bowl/taco/burrito architecture | Moderate: healthful bowl cue, but a same-city operator already owns the position |
| Core overlap | Rice, channa, paneer, chicken, keema, vegetables, yogurt, chutneys | Rice, chickpeas, tandoori meats, kebabs, paneer, cucumber, tomato and yogurt |
| Likely new inventory | Tortillas, cabbage, corn, lime, jalapeño | Tahini, pita, feta, olives, olive oil, parsley and seasoning blends |
| Allergen/holding burden | Wheat/milk already present; cold garnish separated | Tahini adds sesame control; pita/fresh salad need separation and shorten quality window |
| Observed price corridor | Colton conventional burritos about $10.99–$13.50 | Regional bowls about $13.95–$18.79 |
| Central modeled contribution | $4.55/meal at $13.30 realized price | $4.20/meal at $13.80 realized price |
| Recommended role | First fusion pilot | One matched-price control, then seasonal LTO if it performs |

Public restaurant evidence and assumption-based operating model. Mediterranean prices reflect Baladi and Luna Grill; Tikka shows that a Mediterranean–Indian regional position already exists. [47]–[52]

## The fair Mediterranean control

ONE ITEM, SAME EXPOSURE Test a $14.49 Tandoori Chicken Mezze Bowl against the best Indo-Mex bowl: basmati, tandoori chicken, cucumber-tomato-onion salad, raita and a spiced channa dip. Avoid the word “shawarma” unless the process is actually shawarma. If tahini is introduced, sesame becomes an additional major-allergen control. If the control beats the Indo-Mex leader's 30-day repeat rate by at least 10 percentage points, reconsider the sequence.

## Other expansion ideas

| Idea | Role | Why / constraint |
| --- | --- | --- |
| Indian–California wellness bowls | Use now as the operating chassis | Best meal-prep durability and ingredient reuse; nutrition/macronutrient claims wait for recipe analysis |
| Deconstructed family taco kits | Phase two | Strong fit with 3.16-person households; attractive route/order value, but portion and cold-kit assembly must be proven |
| Indo-Chinese bowls | Later limited test | Potential demand, but soy/sesame, wok sauces and crisp textures add allergens and weaken multi-day quality |
| Indian pizza / wings | Do not prioritize | Adds dough, cheese, boxes, equipment and a different production system; regional Indian-pizza competition already exists |
| Fried chaat / nacho mashups | Same-day special only | Social-media appeal, but sogginess, fryer load and component count are poor meal-prep economics |

Appu's, Saucy Chick and Indian Fusion Pizza are category precedents, not direct evidence of Colton demand. [50][51][53]

## Fusion economics and capital discipline

Fusion is not a margin windfall. Its business purpose is to attract net-new customers, raise order size or improve retention. The ranges below extend the proposal's original labor, packaging, direct-channel and 40% vegetarian / 60% meat assumptions; they remain planning estimates until recipes, yields and invoices are validated.

| Per meal | Existing line | Indian–Mexican | Indian–Mediterranean | Indian–California |
| --- | --- | --- | --- | --- |
| Target realized price | $12.30 | $13.00–$13.75 | $13.50–$14.25 | $12.60–$13.20 |
| Ingredient cost | $3.45 | $3.55–$4.05 | $3.85–$4.65 | $3.35–$3.80 |
| Direct production labor | $2.75 | $2.90–$3.10 | $3.05–$3.30 | $2.75–$2.95 |
| Packaging | $0.85 | $0.85–$1.00 | $0.95–$1.15 | $0.85–$0.95 |
| Total variable cost | $8.21 | $8.45–$9.15 | $9.05–$10.15 | $8.20–$8.80 |
| Central contribution | $4.09 | $4.55 | $4.20 | $4.35 |
| Central margin | 33.3% | 34.2% | 30.4% | 34.0% |

## Incremental fusion pilot budget

| Use | Planning allowance |
| --- | --- |
| Recipe development, yield testing and costing | $750–$1,500 |
| Allergen review, labels and nutrition consultation | $400–$1,000 |
| Staff training and paid test batches | $500–$1,200 |
| Cold pans, portion tools and tortilla handling | $400–$1,200 |
| Packaging samples and opening inventory | $400–$1,000 |
| Photography, bilingual ordering-page work and launch marketing | $800–$2,000 |
| Contingency | $500–$1,100 |
| Total incremental Indo-Mex test | $3,000–$8,000 |

CAPITAL RULE Carve this amount from the existing $30,000 pilot authorization; do not add it automatically. If the line needs structural work, new hooded equipment, a dedicated reach-in or material electrical changes, stop, obtain written County direction and re-underwrite the budget.

## Incremental break-even and cannibalization

| Illustration | Indian–Mexican | Indian–Mediterranean | Indian–California |
| --- | --- | --- | --- |
| Illustrative monthly module expense | $500 | $800 | $300 |
| New meals/week to cover module expense | 26 | 44 | 16 |
| Net monthly contribution at 75 new meals/week | $978 | $564 | $1,113 |
| Midpoint startup payback at 75 new meals/week | 5.6 months | 15.1 months | 3.6 months |

Cannibalization warning: at 75 fusion meals per week, a central Indo-Mex case that merely replaces ordinary Maharajah meals loses roughly $350 per month after the added module expense. Track net-new customers, order expansion and cohort retention—not fusion unit sales alone.

## Eight-week fusion validation

1. Co-develop four recipes with an experienced local Mexican cook or consultant; use Spanish proofreading and describe the result as Indo-Mex, not “authentic Mexican.”

2. Run a 40–60-person paid or controlled tasting across current Maharajah customers, nearby Latino households, ARMC/CUSM staff and existing meal-prep buyers.

3. Weeks 1–4: replace two existing weekly choices with one vegetarian and one chicken fusion bowl; produce 25–40 prepaid portions of each, or 50–80 fusion meals per week.

4. Give one Mediterranean control bowl the same price, photo quality, email placement and availability. Compare repeat purchase, not social-media likes.

5. Weeks 5–8: retain only the two best bowls; add at most one taco and one burrito on limited restaurant days if bowl accuracy and production speed are stable.

6. Track fusion orders, first-time customers, substitutions from ordinary meals, assembly seconds, new-inventory waste, ratings, complaints and 30-day reorder by SKU in the POS.

## Advance / revise / stop gates

| Metric | Required result |
| --- | --- |
| Paid evidence | At least 250 fusion meals and 25–30 demonstrably net-new meals per week |
| Economics | At least $4.25 contribution per fusion meal; absolute stop below the proposal-wide $3.50 floor |
| Repeat | At least 50% fusion-specific reorder and at least 60% overall eight-week retention |
| Labor | No more than one additional assembly minute and fewer than eight total production minutes per meal |
| Waste / quality | New-SKU waste below 4%; average flavor score at least 4.3/5; complaints/refunds below 1% |
| Channel / safety | At least 85% direct orders; 100% label accuracy; zero allergen or temperature-control failures |
| Scale trigger | 100 fusion meals/week for four consecutive weeks, including at least 30 net-new meals, before adding more SKUs |
| Mediterranean trigger | Only reconsider as the lead if its matched control produces a repeat rate at least 10 percentage points higher |

The practical launch decision is therefore narrow: two Indo-Mex bowls inside the existing system, not a simultaneous rollout of competing cuisines. Expand only when paid repeat behavior validates the local-market thesis.

# 5. Market and pricing analysis

Fresh Inland Empire meal-prep pricing currently spans roughly $10.99–$20 per meal, with the main competitive cluster around $12.79–$15.99. High-protein plans with 6–8 oz protein often reach $16–$20. Frozen national meals create an $8.50–$10.50 value floor, while nearby Indian restaurant combos cluster around $11–$16. The proposed 10-meal anchors—$10.99 vegetarian and $12.99 nonvegetarian—sit below most fresh local services but above the frozen floor.

Selected regular-price comparators, researched August 8, 2026. Promotions excluded. Package size, protein weight, delivery and format vary. [8]–[16]

| Comparator | Observed regular price / meal | Context |
| --- | --- | --- |
| EasyFit Meals | $14.00 / $13.00 / $12.33 / $11.75 | 5/10/15/20 meals; fresh; protein upgrade +$4 |
| My Healthy Penguin | $13.99 / $13.49 / $13.29 / $12.79 | 5/10/12/20 standard meals; fresh IE delivery |
| Prep Success | $14.99 one-time; $13.49 subscription | Riverside/IE; high-protein positioning |
| Meal Prep Sunday | $12.92 / $12.80 / $12.70 | 5/10/15 meals; free weekly delivery advertised |
| Meal Prep Kingz | $17.00 / $16.50 / $16.00 / $15.50 | 5/10/15/20; six-ounce protein |
| Fit Foods Lifestyle | $18.80 | 10-meal 6 oz plan; Redlands premium |
| Healthy & Fresh Fit | $16.00 / $15.00 / $14.75 | 10/15/20; fresh IE delivery |
| The Meal Preps | $14.99 / $12.99 / $11.99 / $10.99 | 5/8/12/16; $9.99 delivery |
| Clean Eatz | $8.50–$10.50 | Frozen national value floor |
| Nearby Indian combos | $11–$16 | Namaste, Naan Cafe and comparable restaurant substitutes |
| Fresh Indian subscriptions | $11.43–$16 typical observed range | MyTiffinExpress, Sukhmani and other nonlocal comparators |

Prices can change and may exclude tax, shipping, delivery, protein upgrades or promotional discounts. Re-shop the set immediately before launch. [8]–[25]

## Why these prices are competitive

They create a visible saving against Maharajah's current $13–$17.68 curry/biryani entrée range while preserving restaurant value perception. [2]

They undercut most fresh local plans without attempting to match lower-cost frozen products.

They separate vegetarian and meat economics and protect lamb/seafood with surcharges.

The three-tier discount is easy to understand: the same quality, lower price per meal at 10 and 15 meals.

A fallback card is available if cost cards fail: vegetarian $12.49/$11.49/$10.99 and nonvegetarian $14.49/$13.49/$12.99 at 5/10/15 meals.

## Delivery policy

| Channel | Recommended price | Rule |
| --- | --- | --- |
| Restaurant pickup | Free | Default pilot channel |
| Core local route, about 8–10 miles | $6.99 | First drop free on 10+ meals or $100+; preserve route density |
| Extended route, about 10–18 miles | $9.99 | ZIP/day restricted; no one-off long routes |
| Optional second weekly drop | $6.99 core / $9.99 extended | Supports refrigerated freshness for 10/15-meal plans |
| Employer/clinic drop | Free at 20+ meals to one site | One invoice or prepaid individual orders |
| Marketplace | Separate higher price | Avoid for subscriptions; commission is not in base pricing |

## Demand case

Colton, San Bernardino, Riverside and Redlands together had more than 670,000 residents in the Census Bureau's 2025 estimates, but that is not the serviceable market: drive time, route density, income, diet and purchase frequency narrow it substantially. [26]–[29] The practical proof point is smaller. Fifty customers averaging ten meals equal 500 meals per week; 70 such customers equal the base exit rate of 700. A mix of household subscriptions and two or three employer/healthcare drops can reach that scale without mass-market penetration.

# 6. Unit economics and profit potential

The model below uses the proposed price card, an assumed 40% vegetarian / 60% meat mix, production labor of about 6.9 minutes per meal at a loaded $24/hour, and a small net delivery subsidy. It is deliberately more conservative than a food-cost-only restaurant margin because it charges paid batch labor directly to each meal.

| Per meal | Vegetarian | Meat | Blended |
| --- | --- | --- | --- |
| Realized price | $11.10 | $13.10 | $12.30 |
| Ingredients | $2.55 | $4.05 | $3.45 |
| Tray, lid, label, bag | $0.85 | $0.85 | $0.85 |
| Direct production labor | $2.75 | $2.75 | $2.75 |
| Card processing | $0.36 | $0.43 | $0.40 |
| Waste/refunds, 2.5% | $0.28 | $0.33 | $0.31 |
| Utilities/sanitation | $0.20 | $0.20 | $0.20 |
| Net delivery subsidy | $0.25 | $0.25 | $0.25 |
| Total variable cost | $7.24 | $8.86 | $8.21 |
| Contribution per meal | $3.86 | $4.24 | $4.09 |
| Contribution margin | 34.8% | 32.4% | 33.3% |

MARGIN INTERPRETATION Before direct production labor, the blended product margin is about 55.7%; after paid batch labor, contribution is about 33.3%. The proposal should not advertise a 45% all-in variable contribution unless actual recipe, labor and delivery data prove it.

## Break-even

Weekly break-even = monthly fixed cost ÷ (contribution per meal × 4.33).

| Scale | Monthly fixed cost | Contribution / meal | Break-even |
| --- | --- | --- | --- |
| Lean pilot | $4,250 | $3.70 | 265 meals/week |
| Standard | $5,650 | $4.09 | 319 meals/week |
| Growth | $12,000 | $4.65 | 596 meals/week |

At standard economics, 500 meals/week yields about $3,200 monthly line EBITDA; 700 yields about $6,750; 900 yields about $10,300.

## Year-1 scenarios

| Scenario | Weekly ramp | Meals | Revenue | Line EBITDA | Margin |
| --- | --- | --- | --- | --- | --- |
| Conservative | 80 → 300 | 9,872 | $121,431 | –$14,472 | –11.9% |
| Base | 150 → 700 | 22,083 | $271,621 | $25,706 | 9.5% |
| Upside | 200 → 1,700 | 46,764 | $575,197 | $103,272 | 18.0% |

Line EBITDA excludes depreciation, interest, income tax, startup capital and owner distributions. Scenario assumptions are planning estimates.

## Sensitivity warnings

Every $1 price reduction lowers contribution by $1.

Every extra production minute at $24/hour costs $0.40 per meal; two extra minutes move standard break-even from about 319 to about 397 meals/week.

A 10% ingredient-cost shock costs roughly $0.35 per meal.

A $12 free-delivery cost on a ten-meal order is $1.20 per meal, nearly $1 more than the modeled subsidy.

A 25% marketplace commission is about $3.08 on a $12.30 meal and consumes most contribution.

# 7. Startup investment and capital release

| Use of funds | Lean pilot | Standard launch | Growth buildout |
| --- | --- | --- | --- |
| Permits, process/menu review, labeling advice | $1.5k–$4k | $3k–$8k | $8k–$20k |
| Cooling, refrigeration and logging | $3k–$8k | $20k–$45k | $30k–$75k |
| Sealing, labeling, racks, scales, smallwares | $2k–$5k | $6k–$15k | $25k–$60k |
| Dedicated buildout | — | As needed | $40k–$100k |
| Delivery equipment / vehicle | Insulated totes | Mostly outsourced | $20k–$70k |
| E-commerce, POS, photography, brand | $1k–$3k | $3k–$10k | $10k–$25k |
| Opening inventory and packaging | $1.5k–$3k | $3k–$7k | $8k–$15k |
| Launch marketing | $2k–$5k | $6k–$15k | $20k–$50k |
| Working capital and contingency | $5k–$9k | $9k–$20k | $35k–$85k |
| Total | $16k–$37k | $50k–$120k | $200k–$500k |

Planning ranges, not vendor quotes. Standard and growth totals are cumulative business cases, not immediate spending recommendations.

## Recommended release schedule

1. Pilot authorization — up to $30,000. County consultation, recipe/label system, cooling test, smallwares, packaging, ordering page, opening inventory, modest marketing and working capital.

2. Conditional standard capital — only after four consecutive weeks above 300 meals, zero cooling/delivery temperature failures, ≥60% eight-week retention and ≥$3.50 contribution per meal.

3. Growth capital — only after sustained 900+ meals/week, demonstrated kitchen congestion or wholesale/B2B contracts that justify dedicated space and equipment.

At the base month-12 rate of 700 meals/week, annualized line EBITDA is approximately $81,000. A standard midpoint investment around $80,000–$85,000 may achieve simple payback in roughly 20–24 months from launch if the exit run rate and retention continue. This is not a guaranteed return.

# 8. Regulatory, safety and labeling plan

GET A WRITTEN COUNTY ROUTE DETERMINATION San Bernardino County states that plans are required when the operation type or menu changes. Do not assume the existing restaurant permit automatically covers prepacked subscriptions, cold-route delivery, wholesale placement or reduced-oxygen packaging. [30]–[34]

## Likely regulatory route

| Sales route | Likely treatment | Action |
| --- | --- | --- |
| Pickup by end customer | Retail food operation | County approval of menu, process, cold storage, packaging and labels under existing permit |
| Maharajah delivery to end customer | Retail + transport controls | Add delivery/cold-chain SOP and route logs |
| Third-party delivery | Retail + delivery rules | Tamper-evident closure before handoff |
| Gyms, stores or other resellers | Likely wholesale | County wholesale permit + CDPH PFR may apply |
| Vacuum/MAP/cook-chill | Specialized process | County-approved HACCP plan may be required |
| Interstate shipping | Expanded processing/distribution | Separate federal, state, carrier and label analysis |

The June 30, 2026 County fee schedule lists Public Eating Place plan-change fees of $885/$961/$1,002 by facility size, with separate fees for remodels, annual permits and consultation. Exact classification belongs to EHS. [31]

## Cooling and cold-chain controls

Cool cooked TCS food from 135°F to 70°F within two hours and to 41°F within a total of six hours. [41]

Use shallow pans, small batch depth, cooling wands/ice baths and verified rapid-cooling or walk-in capacity.

Log cook temperature, two cooling checkpoints, packaging temperature, cooler temperature, dispatch temperature and delivery exceptions by lot.

Operate to 41°F maximum cold holding, with a target dispatch temperature of 38–40°F.

Use calibrated probes and route data-loggers during validation.

Use conventional sealed trays during pilot; do not use vacuum or modified-atmosphere packaging until the County approves the process.

## Shelf-life policy

USDA consumer guidance recommends using cooked refrigerated leftovers within three to four days. [7] The safest launch promise is therefore Fresh 4 + Frozen remainder or a second weekly drop. Seafood should be short-dated or frozen. Day-1/day-3/day-4 and freeze-thaw sensory tests are required for each recipe family.

## Label minimum

Common/descriptive product name.

Ingredients in descending order by weight, including sub-ingredients.

Major allergen declaration; never rely on “may contain” instead of controls.

Accurate net quantity and business name/place.

Lot/batch code, packed date and USE by date.

Perishable—keep refrigerated; freeze/thaw/reheat instructions; reheat to 165°F.

Nutrition Facts and macro claims only after the applicable exemption/requirement is confirmed and recipes are analyzed.

Since July 1, 2026, California date-label language for newly manufactured food uses BEST if Used by for quality or USE by for safety; consumer-facing sell-by language is prohibited. [35][36]

## Sales tax and POS

Hot prepared food is generally taxable; cold food sold to go can be nontaxable, but the restaurant 80/80 rule and separate-accounting election matter. Create distinct POS keys for cold meal-prep pickup, cold delivery, hot restaurant food, taxable add-ons and nontaxable items, then obtain written CDTFA guidance. Colton's combined rate was 8.75% as of July 1, 2026; destination rules can differ. [37][38][42]

# 9. Operating model

## Capacity and staffing

| Stage | Practical capacity | Pattern | Incremental team |
| --- | --- | --- | --- |
| Lean | 150–300/week | One production/pack day | Existing lead allocation; 1 prep/packer; 4–8 coordinator hours |
| Standard | 400–900/week | Two production days; dedicated cooling/pack window | 0.5–0.75 lead-cook FTE; 1.5–2 prep/pack FTE; 0.25 QA/coordinator |
| Growth | 1,200–2,000/week | Three to four production days | Production manager; 2 cooks; 3–4 prep/pack; QA/inventory/customer support |

## Sample weekly workflow

| Timing | Control |
| --- | --- |
| Thursday 8 p.m. | Order cutoff; payment captured; production count frozen |
| Friday | Procurement, receiving, supplier-label capture and batch sheets |
| Lowest-volume restaurant window | Prep and cook; choose day from POS hourly sales, not assumption |
| Same day | Rapid cooling with logged checkpoints; packaging only at approved temperature |
| Monday/Tuesday | Pickup and dense core delivery route |
| Thursday optional | Second production/drop for 10/15-meal customers who do not want frozen remainder |
| Following day | Waste, temperature, complaint, labor-minute and contribution reconciliation |

## Operational KPIs

| Metric | Pilot gate |
| --- | --- |
| Contribution after paid production labor | ≥$3.50 per meal |
| Ingredient cost | ≤28% blended |
| Packaging | ≤7% |
| Waste/refunds | <4% pilot; <3% mature |
| Eight-week reorder/retention | ≥60% |
| Direct-order share | ≥85% |
| On-time fulfillment | ≥95% |
| Label accuracy | 100% |
| Cooling/delivery temperature failures | Zero |
| Customer complaint rate | <1% |

# 10. Go-to-market plan

## Priority customers

Current Maharajah customers and rewards members: lowest-cost first buyers.

Busy healthcare workers in the Loma Linda, Colton and San Bernardino corridors.

University faculty, staff and graduate students.

Vegetarian and Indian households wanting weekday convenience without generic fitness food.

Gym/fitness customers who value measured portions—but only after recipes/macros are validated.

Small employers, clinics and dental/medical offices that can support a dense weekly drop.

## Eight-week beta

1. Recruit 40–60 households from rewards, catering and direct-order contacts; cap the first production run.

2. Offer a five-meal sampler at no more than 15% off. Avoid extreme first-box discounts.

3. Use weekly ordering with optional auto-renew; make skipping and cancellation simple.

4. Collect a one-minute post-meal score: flavor, portion, spice, reheating, packaging and reorder intent.

5. Run referral credit only after the referring customer's second paid order.

6. Publish menu, ingredients, allergens, pack/use-by date and reheating information before checkout.

## Channel economics

The direct website/app should be the subscription system of record. Third-party apps can be used for discovery or one-time trial at a separately marked-up price, but not as the economic foundation. Employer drops are attractive because 20–50 meals can be delivered to one location with one cold-chain event.

# 11. 90-day implementation roadmap

| Window | Objective | Deliverables |
| --- | --- | --- |
| Days 1–14 | Permission and truth | County preliminary consultation; tax/insurance review; recipe inventory; resolve digital-menu errors; cooling-load test plan |
| Days 15–30 | Build the operating system | 12 standardized SKUs; recipe yields/costs; allergen matrix; labels; trays; lot logs; packaging/reheating tests; four fusion bench recipes |
| Days 31–45 | Pre-sell | Paid bilingual fusion tasting; photos/order page; rewards/email/SMS campaign; recruit beta households; schedule route; staff drills |
| Days 46–75 | Controlled beta | 150–250 meals/week; pickup + one route; weekly P&L and safety review; freeze-thaw testing |
| Days 76–90 | Gate decision | Scale, reprice, simplify or pause based on contribution, retention, safety, labor minutes and restaurant impact |

## Go / revise / stop rules

| Decision | Trigger |
| --- | --- |
| GO to standard launch | Four weeks >300 meals; ≥$3.50 contribution; ≥60% retention; zero temperature failures; ≥95% on-time; no material restaurant harm |
| REVISE and retest | Demand exists but contribution is <$3.50, labor exceeds 8 minutes/meal, waste >4%, or price/package conversion is weak |
| STOP / remain pilot-only | Temperature failure, labeling unreliability, persistent restaurant disruption, <40% retention, or inability to approach 250 meals/week |

# 12. Key risks and mitigations

| Risk | Early warning | Mitigation |
| --- | --- | --- |
| Unsafe cooling | Rice/curry misses logged time-temperature target | Smaller batches; shallow pans; blast chiller; stop production until corrected |
| Margin erosion | Labor >8 min/meal; ingredient >28%; delivery >10% | Reduce SKUs; surcharge premium proteins; reprice; dense routes |
| Low retention | Eight-week reorder <60% | Improve rotation, portion, spice and quality before increasing marketing |
| Allergen/label error | Ingredient changes not reflected on label | Supplier-label control, locked recipes, dual-check print/pack process |
| Restaurant cannibalization | Peak ticket times/overtime worsen | Separate production windows, dedicated labor/cold storage, capacity cap |
| Shelf-life complaints | Texture declines after day 3–4 | Fresh 4 + Frozen remainder; split delivery; remove weak dishes |
| Menu confusion | Support contacts about duplicate names/prices | Clean current digital menu before new storefront |
| Fusion brand dilution | Customers cannot tell traditional from fusion items | Separate Masala Street sub-menu; keep Indian recipes and parent-brand attribution explicit |
| Cultural credibility | Feedback describes the line as gimmicky or inauthentic | Co-develop with Mexican culinary talent; Spanish proofread; say Indo-Mex, not authentic Mexican |
| Fusion cannibalization | Fusion units rise but new customers/order size do not | Track cohorts and substitutions; require 25–30 net-new meals/week before scale |
| Fusion menu bloat | More than four fillings/eight additions or assembly >1 minute | Two weekly slots, shared garnish system and automatic SKU pruning |
| Capital overreach | Equipment purchased before demand proof | Milestone-based release; rent/lease where sensible; preserve cash reserve |

# 13. Final recommendation

THE INVESTABLE VERSION A prepaid, direct-to-consumer, pickup-plus-dense-route beta with six vegetarian and six nonvegetarian choices per week; three quantity tiers; premium-protein surcharges; validated cooling and labels; and no wholesale or reduced-oxygen packaging. Within the 12 weekly slots, test one vegetarian and one chicken Indo-Mex bowl. Fund $30,000 now, not $120,000; carve the fusion test from that cap.

The proposal is a cautious “yes.” Maharajah's existing brand, menu breadth and batchable sauces create a credible product advantage. The financial model is not robust at low volume: the conservative case loses money, and the base case only becomes attractive after repeat volume clears roughly 300–320 meals per week. Fusion is strategically useful only if it brings net-new customers, larger orders or better retention; replacing ordinary meal sales with slightly higher-cost fusion does not create value. The business should prove volume, quality and food safety before committing to standard-scale refrigeration, sealing, delivery or dedicated space.

The decisive next action is not a broad menu launch. It is a two-hour working session with the owner, chef, County EHS and the last 90 days of POS/labor data to validate kitchen capacity, low-volume production windows, recipe costs, cooling and the 12 launch SKUs—then a paid, bilingual fusion tasting with an experienced Mexican culinary collaborator. Once that truth set exists, the beta can be on sale in approximately 45 days.

# Appendix A. Complete current public menu audit

All names and prices below were retrieved from Maharajah's official direct-order menu on August 8, 2026. Audit notes paraphrase public descriptions and add meal-prep/reconciliation observations. The official page has 135 non-Popular rows across 16 categories; apparent counts and duplicates are retained rather than silently corrected. [2]

## Appetizers

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Potato Pakoda | $6.24 | Fried potato; poor chilled fit |
| Onion Pakoda | $7.28 | Fried onion; poor chilled fit |
| Chili Pakoda | $8.32 | Fried chili; spicy; poor chilled fit |
| Chicken Pakoda | $9.36 | Fried chicken; poor chilled fit |
| Cheese Pakoda | $8.32 | Milk; fried |
| Spinach Pakodas | $8.32 | Spinach + gram flour; fried |
| Mixed Vegetables Pakoda | $14.00 | Eggplant, spinach, onion, pepper, potato; fried |
| Methu Vada | $10.39 | Likely lentil fritter; spelling should be Medu Vada |
| Masala Vada | $10.39 | Likely lentil/chickpea fritter |
| Meat Samosas | $9.36 | Site says ground chicken; third-party page says beef; verify |
| Vegetable Samosas | $8.32 | Potato, carrot, pea; wheat pastry |
| Potato Bonda | $8.32 | Spiced potato fritter |
| Samosa Chaat | $9.36 | Samosa, channa, yogurt, chutneys |
| Onion Chili Pakoda | $9.36 | Chili, onion, cilantro, lemon; fried |
| Fish Fry | $10.40 | Tilapia, spice, onion, cilantro; short-dated only |

## Soups, Salad & Pickles

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Sambar | $5.20 | Lentil-vegetable soup; strong separated meal-prep side |
| Rasam | $5.20 | Tamarind-spice soup; verify recipe |
| Tossed Green Salad | $5.20 | Cold; dressing choice; separate cup |
| Indian Style Hot Salad | $5.20 | Tomato, green chili, onion |
| Raita | $4.16 | Milk: yogurt, cucumber, chili, tomato, onion |
| Plain Yogurt | $2.08 | Milk |
| Pickle | $2.07 | Verify oil, mustard, preservative, allergen labels |
| Onion & Chilis | $1.04 | Fresh garnish; separate cold cup |
| Chutney | $1.00 | Coconut, tomato, mint or tamarind; verify peanuts/tree nuts |

## Chicken A La Carte

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Chicken Curry | $14.56 | High meal-prep fit |
| Chicken Masala Curry | $14.56 | High fit; verify nuts/dairy |
| Chicken Korma | $14.56 | High fit; likely milk + tree nuts |
| Chicken Saag | $14.56 | High fit; spinach base; possible milk |
| Chicken Vindaloo | $14.56 | High fit; spicy; verify cashew/nuts |
| Chicken Makhani / Butter Chicken | $15.00 | High fit; milk + likely cashew |
| Chicken Tikka Masala | $15.60 | High fit; milk + likely cashew |
| Chicken Curry | $14.56 | Duplicate display; internal slug appears to be Andhra Chicken Fry |
| Chicken Keema | $15.14 | High fit; minced chicken |
| Chicken Shish Kabob | $16.64 | Conditional; can dry on reheating |

## Lamb A La Carte

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Lamb Curry | $16.64 | High fit; premium +$3 |
| Lamb Saag | $16.64 | High fit; premium +$3; possible milk |
| Lamb Vindaloo | $16.00 | High fit; premium +$3; spicy |
| Lamb Korma | $16.64 | High fit; premium +$3; milk + tree nuts |

## Beef A La Carte

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Beef Curry | $16.64 | High fit; verify nuts |
| Beef Saag | $16.64 | High fit; possible milk |
| Beef Korma | $16.64 | High fit; milk + tree nuts |
| Beef Vindaloo | $16.64 | High fit; spicy; verify nuts |
| Beef Keema | $16.64 | High fit; minced beef |

## Seafood A La Carte

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Shrimp Masala | $17.68 | Shellfish; short-dated/frozen premium +$2 |
| Shrimp Saag | $17.68 | Shellfish; possible milk; short-dated |
| Shrimp Vindaloo | $17.68 | Shellfish; spicy; short-dated |
| Fish Masala | $17.68 | Fish; short-dated/frozen premium +$2 |
| Fish Saag | $17.68 | Fish; possible milk; short-dated |
| Fish Vindaloo | $17.68 | Fish; spicy; short-dated |

## Biryani A La Carte

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Chicken Biryani | $16.64 | High fit with rapid rice cooling |
| Lamb Biryani | $17.68 | High fit; premium +$3 |
| Beef Biryani | $17.68 | High fit |
| Shrimp Biryani | $17.68 | Shellfish; short-dated/frozen |
| Vegetable Biryani | $15.60 | High vegetarian fit |
| White Rice | $4.16 | Rapid cooling required |
| Basmati Rice | $4.16 | Rapid cooling required |
| Hyderabadi Chicken Biryani | $16.64 | High fit |
| Hyderabadi Chicken Biryani | $12.48 | Duplicate public name; internal weekend-special SKU |

## Vegetarian A La Carte

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Dhal Curry | $13.00 | Lentils, spinach, tomato, onion, spice; strong core SKU |
| Vegetable Masala | $13.52 | High fit; verify nuts/dairy |
| Mutter Paneer | $14.56 | Milk; standardize spelling to Matar Paneer |
| Aloo Gobi | $13.52 | Cauliflower, potato, tomato, onion, spice; strong core |
| Aloo Mutter | $13.52 | Potato + peas; standardize spelling to Aloo Matar |
| Baingan Bartha | $13.52 | Roasted eggplant, onion, tomato, spice; standardize Bharta |
| Channa Masala | $13.52 | Chickpeas, tomato, herbs, spice; strong core |
| Mushroom Masala | $13.52 | Conditional texture; verify nuts/dairy |
| Saag Paneer | $14.56 | Milk; strong sauced premium SKU |
| Potato Curry | $13.52 | High fit; lower protein |
| Malai Kufta | $14.56 | Milk/nuts likely; fried kofta; standardize Kofta |
| Aloo Saag | $13.52 | Site states cream; milk |
| Channa Saag | $13.52 | Chickpea + spinach; strong core |
| Paneer Tikka Masala | $15.60 | Milk + likely tree nuts; strong premium |
| Vegetable Korma | $13.52 | Milk + tree nuts likely; high fit |
| Channa Masala | $14.56 | Duplicate public label; internal slug appears to be Chole Bhatura |
| Dhal Makhani | $13.00 | Milk likely; strong core; standardize Dal |

## Tandoori Specials

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Paneer Tikka Dry | $14.00 | Milk; conditional reheating; premium |
| Royal Feast | $22.88 | Mixed chicken/lamb; useful performance concept, not base plan |
| Tandoori Chicken Half | $11.44 | Two leg quarters; milk likely in marinade |
| Tandoori Chicken Full | $18.00 | Four leg quarters; milk likely in marinade |
| Tandoori Shrimp | $17.68 | Shellfish; short-dated premium |
| Chicken Tikka Dry | $15.60 | Chicken breast, pepper, onion; conditional reheating |
| Chili Chicken | $18.00 | Possible soy/wheat; fried according to third-party listing |
| Chicken Tikka Dry | $16.22 | Duplicate display; internal Chicken Tikka Kabob SKU |
| Chicken Tikka Dry | $16.22 | Duplicate display; internal Chicken Shish Kabob SKU |
| Tikka Dry | $17.91 | Description identifies lamb; rename Lamb Tikka Kabob |
| Chicken Shish Kabob | $16.64 | Also listed under Chicken |

## Madras Specialties

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Masala Dosa | $11.44 | Poor chilled fit; same-day add-on |
| Moong Dosa | $12.48 | Poor chilled fit |
| Moong Masala Dosa | $12.48 | Poor chilled fit |
| Rava Crispy Dosa | $13.52 | Wheat/semolina; poor chilled fit |
| Rava Masala Dosa | $14.56 | Wheat/semolina; poor chilled fit |
| Mysore Masala Dosa | $12.48 | Coconut/tomato chutney; poor chilled fit |
| Uttapam | $14.56 | Conditional; poor multi-day texture |
| 4 PC Idli | $5.20 | Moderate fit; test day-3 texture |
| Idli Sambar (1 piece) | $5.20 | Moderate if packed separately |
| Idli Sambar (2 piece) | $6.24 | Moderate if packed separately |
| 1 Pc Vada Sambar | $5.20 | Fried; poor multi-day texture |
| Vada Sambar (2 piece) | $6.24 | Fried; poor multi-day texture |
| Cheese Dosa | $11.44 | Milk; poor chilled fit |
| Plain Dosa | $10.40 | Poor chilled fit |
| Egg Dosa | $11.44 | Egg; poor chilled fit |
| 4 PC Masala Vada | $6.24 | Fried; poor chilled fit |
| 4 Pc Methu Vada | $6.49 | Fried; standardize Medu Vada |

## Andhra Specials

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Idli Sambar Special | $15.59 | Components not described on direct menu |
| Vada Sambar Special | $17.67 | Components not described on direct menu |

## Fresh Bread

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Papadam | $3.12 | Lentil wafer; pack dry separately |
| Poori | $4.16 | Wheat; fried; poor chilled fit |
| Paratha | $4.16 | Wheat; freeze separately |
| Aloo Paratha | $5.20 | Wheat + potato; freeze separately |
| Naan (Plain) | $3.12 | Wheat; possible milk/egg; freeze separately |
| Garlic Naan | $3.12 | Wheat; possible milk/egg |
| Garlic Chili Naan | $4.16 | Wheat; possible milk/egg |
| Keema Naan | $5.20 | Wheat + meat; verify meat identity |
| Onion Kulcha | $5.20 | Wheat; possible milk |
| Chapati / Roti | $4.33 | Wheat; best bread add-on for meal prep |

## Lassi & Related Drinks

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Plain Lassi | $3.12 | Milk/yogurt |
| Mango Lassi | $3.12 | Milk/yogurt |
| Pineapple Lassi | $3.12 | Milk/yogurt |
| Strawberry Lassi | $3.12 | Milk/yogurt |
| Mango Juice | $3.12 | Check added sugar/preservatives |

## Lassi & Related Drinks (continued)

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Bottled Water | $2.08 | Packaged beverage |

## Hot Beverages

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Spicy Indian Tea | $3.12 | Likely milk; same-day only |
| Madras Special Coffee | $3.12 | Likely milk; same-day only |
| Black Tea or Coffee | $2.08 | Same-day only |
| Indian Style Iced Coffee | $3.12 | Likely milk; cold add-on |

## Cold Beverages

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Diet Coke | $3.12 | Packaged/fountain beverage |
| Sprite | $3.12 | Packaged/fountain beverage |
| Iced Tea | $3.12 | Cold beverage |
| Lemonade | $3.12 | Cold beverage |
| Orange Fanta | $3.12 | Packaged/fountain beverage |
| Coke | $3.12 | Packaged/fountain beverage |

## Desserts

| Menu item | Direct price | Audit / meal-prep note |
| --- | --- | --- |
| Kulfi | $4.16 | Milk + tree nuts likely; frozen add-on |
| Gulab Jamun (2 piece) | $3.12 | Milk + wheat likely; separate add-on |
| Kheer | $3.12 | Milk, rice, raisins/nuts likely; cold add-on |
| Mango Kulfi | $4.16 | Milk + possible tree nuts; frozen |
| Pistachio Kulfi | $4.16 | Milk + pistachio; frozen |

# Appendix B. Source register and research method

Research date: August 8, 2026. Public prices are regular displayed prices where possible; promotions were excluded from the sustainable benchmark. Competitor portions, shipping, tax, delivery, subscriptions and geographic eligibility differ. Official restaurant and government sources were prioritized. Ingredient statements not published by Maharajah are labeled as secondary or inferred and must be checked against recipes and supplier labels.

[1] Maharajah India Cuisine homepage

[2] Maharajah official direct-order menu

[3] Maharajah story

[4] Maharajah catering

[5] Maharajah Uber Eats listing (secondary data only)

[6] FDA food allergens

[7] USDA leftovers and food safety

[8] EasyFit Meals 5-meal pack

[9] My Healthy Penguin standard plan

[10] Prep Success Meals

[11] Meal Prep Sunday

[12] Meal Prep Kingz Chef's Choice

[13] Fit Foods Co

[14] Healthy & Fresh Meal Prep

[15] The Meal Preps plans

[16] Clean Eatz Riverside meal delivery

[17] Namaste India Cafe menu

[18] Naan Cafe

[19] Indian Eats menu

[20] India's Clay Oven menu

[21] Gandhi Indian Cuisine order page

[22] MyTiffinExpress

[23] Sukhmani Foods plans

[24] Tiffin Bay menu

[25] CookUnity cost and delivery

[26] U.S. Census QuickFacts: Colton

[27] U.S. Census QuickFacts: San Bernardino

[28] U.S. Census QuickFacts: Riverside

[29] U.S. Census QuickFacts: Redlands

[30] San Bernardino County plan-check FAQ

[31] San Bernardino County EHS fee schedule

[32] San Bernardino County food facilities

[33] CDPH Processed Food Registration

[34] CDPH retail HACCP guidance

[35] California retail food-label guide

[36] California AB 660 date-label law

[37] CDTFA restaurant tax guide

[38] CDTFA Regulation 1603

[39] California minimum wage

[40] San Bernardino County food handlers and managers

[41] FDA cooling cooked TCS food

[42] CDTFA current sales-tax rates

[43] Arrowhead Regional Medical Center: about the hospital

[44] California University of Science and Medicine: 2029 white-coat class

[45] El Rey Express Mexican Grill Colton direct-order menu

[46] Tacos Y Mas Colton direct-order menu

[47] Chick-N-Falafel Colton

[48] Luna Grill Riverside direct-order menu

[49] Baladi Riverside menu

[50] Appu's Turmeric Cafe direct-order menu

[51] Saucy Chick Indi-Mex Eatery direct-order menu

[52] Tikka Mediterranean & Indian Fusion

[53] Indian Fusion Pizza Riverside listing

# Appendix C. Assumptions and limitations

No access was available to Maharajah's recipes, supplier invoices, sales mix, kitchen layout, cooler capacity, payroll, lease, insurance, POS reports or customer list.

Ingredient, allergen and recipe-family analysis is not a substitute for chef-verified formula sheets and supplier documentation.

Startup ranges are planning estimates; written vendor quotes and plan-check determinations are required.

Pro forma profit is incremental to the meal-prep line and excludes depreciation, debt, income tax, owner distributions and unmeasured cannibalization/opportunity cost.

The proposal is business planning, not legal, tax, accounting, food-science or regulatory advice.

Prices and regulations can change; competitor prices should be rechecked immediately before launch.